## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | As a developer, I want to set up JDBC + MySQL connection so that the application can store all banking data securely. | MUST HAVE | None | Greeshmitha | 3- Completed
1 | 1 | US02 | As a user, I want to create an account with username, password, and email so that I can use the banking simulator. | MUST HAVE | US01 | Greeshmitha | 3- Completed
1 | 1 | US03 | As a user, I want to log in using my credentials so that I can access my bank account. | MUST HAVE | US02 | Greeshmitha | 3- Completed
1 | 1 | US04 | As a user, I want to reset/forget my password using email OTP so that I can recover my account. | SHOULD HAVE | US02 | Greeshmitha | 3- Completed
2 | 2 | US05 | As a user, I want to view my bank account details so that I can know my balance and information. | MUST HAVE | US03 | Greeshmitha | 3- Completed
2 | 2 | US06 | As a user, I want to deposit money so that my account balance increases. | MUST HAVE | US05 | Greeshmitha | 3- Completed
2 | 2 | US07 | As a user, I want to withdraw money with validation so that I don’t overdraft. | MUST HAVE | US06 | Greeshmitha | 3- Completed
2 | 2 | US08 | As a user, I want to delete my user profile without deleting my bank account so that my account remains preserved. | COULD HAVE | US02 | Greeshmitha | 3- Completed
3 | 3 | US09 | As a user, I want to view my transaction history so that I can track my financial activities. | MUST HAVE | US06/US07 | Greeshmitha | 3- Completed
3 | 3 | US10 | As a user, I want email alerts for transactions so that I stay informed about activities in my account. | SHOULD HAVE | US09 | Greeshmitha | 3- Completed
3 | 3 | US11 | As a user, I want a balance alert system when the balance is low so that I can avoid failed transactions. | COULD HAVE | US10 | Greeshmitha | 3- Completed
4 | 4 | US12 | As a user, I want to update my profile details (username/password) so that my information stays current. | MUST HAVE | US03 | Greeshmitha | 3- Completed
4 | 4 | US13 | As a user, I want the system to logout automatically after password change for security. | MUST HAVE | US12 | Greeshmitha | 3- Completed
4 | 4 | US14 | As a developer, I want the deletion of bank accounts to cascade (delete users + transactions) so that the database remains clean. | SHOULD HAVE | US08 | Greeshmitha | 3- Completed
4 | 4 | US15 | As a tester, I want full system end-to-end testing scenarios so that final deployment is stable. | MUST HAVE | ALL | Greeshmitha | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7